## Project Overview & Team
NETSENTINEL: REAL-TIME NETWORK SECURITY MONITORING & IDS
12-Week Comprehensive Academic Plan, Weekly Progress Reports & Daily Diary (July 6, 2026 – September 26, 2026)
PROJECT ADMINISTRATIVE DETAILS
Project Title | NetSentinel (Enterprise-Grade Real-Time Intrusion Detection System)
Project Guide | Er. Ram Babu Buri (Associate Professor / Project Supervisor)
Research Domain | Network Security, Heuristic Anomaly Detection & High-Concurrency Systems
Duration & Scope | 12 Academic Weeks (6 Days/Week, 72 Operating Days)
Target Completion | Week 12 (Final Demonstration, Defense, Evaluation & Submission)
Architecture | Zero-Dependency Multi-Module Java 21 LTS + Spring Boot 3 + Project Loom + SQLite
SOC Web Interface | Single-Page Dark SOC Dashboard (5 Telemetry Views, Chart.js, 3D WebGL Globe)
Code Repositories | Dual-Mirrored Git Repositories (Verified SHA-256 Byte Integrity)
TEAM MEMBERS & MODULE ASSIGNMENTS
Member # | Full Name | Student ID | Official Email | Assigned Module | Core Technology | Scope of Responsibility | Status
1 | Nandlal Upman | 24E1ARADM40P108 | naveensharmardx@gmail.com | Module 1: Packet Capture & Ingestion | Java 21, Libpcap, Virtual Threads | Pure Java PCAP parser, 4-port decoy honeypots (2222, 8088, 8888, 9090), packet generator | Completed
2 | Piyush Agarwal | 24E1ARADM40P120 | piyushagarwal13042006@gmail.com | Module 2: Rule-Based Detection Engine | Java 21, Sliding Deques, Heuristics | ArrayDeque sliding windows, Port Scan, SYN Flood, Brute Force rules, alert cooldown | Completed
3 | Mayank Jangid | 24E1ARADM30P097 | jangidmayank094@gmail.com | Module 3: Anomaly & ML Detection Engine | Java 21, Shannon Entropy, Isolation Forest | Flow aggregation, Shannon port entropy, SYN/ACK ratios, unsupervised ML anomaly inference | Completed
4 | Nikhil Kumar | 24E1ARADM30P110 | nikhil.its.rio@gmail.com | Module 4: Central Backend & SQLite Storage | Spring Boot 3, SQLite (WAL), Loom | REST APIs (/api/alerts, /traffic-stats), SQLite schema, 1Hz rolling buffer, coordinator | Completed
5 | Parikshit Vyas | 24E1ARADM40P119 | vparikshit32@gmail.com | Module 5: SOC Web Dashboard & Frontend | HTML5, CSS3, ES6 JS, Chart.js, Three.js | Dark SOC single-page UI, 5 telemetry views, MITRE ATTACK matrix, 3D Cyber Threat Globe | Completed

## 12-Week Master Plan
NETSENTINEL: 12-WEEK MASTER ACADEMIC PROJECT ROADMAP
Week # | Start Date | End Date | Project Phase | Milestone / Focus Area | Key Technical Deliverables | Target Modules | Lead Members | Status
Week 1 | 06-Jul-2026 | 11-Jul-2026 | Phase 1: Inception | Project Definition & SRS Formulation | Literature survey (Snort/Zeek), scope definition, team division, Guide approval | All Modules | All 5 Members | 100% Completed
Week 2 | 13-Jul-2026 | 18-Jul-2026 | Phase 1: Architecture | Requirements & Frozen Schema Contracts | User roles, SRS document, frozen Packet JSON and Alert JSON contracts, tech stack selection | Contracts / Core | Nandlal, Nikhil | 100% Completed
Week 3 | 20-Jul-2026 | 25-Jul-2026 | Phase 1: Design | UML System Modeling & Architecture | Master pipeline flowchart, Sequence diagrams, State machine, Class diagrams | Core Design | Piyush, Mayank | 100% Completed
Week 4 | 27-Jul-2026 | 01-Aug-2026 | Phase 1: Foundation | Database DDL Schema & SOC Wireframes | SQLite relational schema (alerts, packets), WAL mode indexing, SOC wireframing, dark theme CSS | Module 4 & 5 | Nikhil, Parikshit | 100% Completed
Week 5 | 03-Aug-2026 | 08-Aug-2026 | Phase 2: Core Engineering | Packet Ingestion & Rule-Based Detection | Pure Java PcapBinaryParser, 4-port decoy honeypots, sliding ArrayDeque rule engine (Port scan, SYN flood) | Module 1 & 2 | Nandlal, Piyush | 100% Completed
Week 6 | 10-Aug-2026 | 15-Aug-2026 | Phase 2: Core Engineering | Flow Anomaly ML & Spring Boot Backend | Shannon port entropy, SYN/ACK ratio analysis, Isolation Forest ML engine, Spring Boot REST controllers | Module 3 & 4 | Mayank, Nikhil | 100% Completed
Week 7 | 17-Aug-2026 | 22-Aug-2026 | Phase 2: Frontend Engineering | SOC Dashboard & Real-Time Telemetry | Single-page dashboard, Chart.js live traffic graphs, Web Audio alarms, PCAP inspector, Pause/Live triage | Module 5 | Parikshit | 100% Completed
Week 8 | 24-Aug-2026 | 29-Aug-2026 | Phase 2: Advanced Views | MITRE ATTACK Matrix & 3D Threat Globe | MITRE ATTACK vector coverage grid, interactive WebGL 3D Globe with ballistic attack arcs, offline textures | Module 5 | Parikshit, Nikhil | 100% Completed
Week 9 | 31-Aug-2026 | 05-Sep-2026 | Phase 3: Integration & Testing | Full System Integration & Concurrency Stress | Inter-module pipeline orchestration, JUnit 5 + MockMvc suites, 1,000 pkts/sec stress testing, memory leak profiling | All Modules | All 5 Members | 100% Completed
Week 10 | 07-Sep-2026 | 12-Sep-2026 | Phase 3: Network Deployment | Live LAN Deployment & Decoy Attack Simulation | Multi-machine Wi-Fi/LAN testing, curl http://192.168.1.5:8088 probing, dual-engine honeypot verification, IP cleanup | Module 1, 2, 4 | Nandlal, Piyush, Nikhil | 100% Completed
Week 11 | 14-Sep-2026 | 19-Sep-2026 | Phase 3: Optimization & Audit | Dynamic Interceptions Sync & Export Reports | MITRE ATTACK dynamic filtering (empty when cleared), 1-click CSV Report & JSON Audit exports, mirror repo sync | Module 4 & 5 | Nikhil, Parikshit | 100% Completed
Week 12 | 21-Sep-2026 | 26-Sep-2026 | Phase 3: Final Delivery | Production Packaging & Final Defense Submission | Single-click executable JAR (Fat JAR), run.bat launcher, comprehensive report, Viva slides, Guide sign-off | System-Wide | All 5 Members | 100% Completed

## Weekly Progress Reports
NETSENTINEL: DETAILED WEEKLY ACADEMIC PROGRESS REPORTS (WEEKS 1 TO 12)
Week # | Period & Phase | Weekly Objectives | Actual Work Accomplished | Module Member Contributions | Technical Challenges & Solutions | Guide Verification Status
Week 1 | 06-Jul-2026 to 11-Jul-2026 Phase 1: Inception | Define project scope, survey literature on intrusion detection, divide team roles, and obtain Project Guide approval. | • Conducted comparative survey of Snort, Suricata, and Zeek. • Established design requirement for pure Java without WinPcap/Npcap root dependencies. • Defined 5 isolated processing modules and established project Git repository. • Project Guide Er. Ram Babu Buri approved project proposal and system scope. | • Nandlal: Surveyed binary packet capture standards. • Piyush: Researched sliding-window detection algorithms. • Mayank: Investigated statistical anomaly metrics. • Nikhil: Configured Maven multi-module parent POM. • Parikshit: Drafted initial SOC UI design objectives. | Challenge: Eliminating platform-specific C capture drivers. Solution: Commited to pure Java byte-level libpcap dissection and Virtual-Thread decoy honeypot listeners. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 11-Jul-2026
Week 2 | 13-Jul-2026 to 18-Jul-2026 Phase 1: Architecture | Develop detailed Software Requirements Specification (SRS), formalize user roles, and freeze JSON communication contracts. | • Formulated comprehensive SRS covering Functional & Non-Functional Requirements. • Enforced strict Role-Based Access: Security Analyst, Network Admin, Simulated Attacker. • Authored and froze immutable JSON schemas: Packet JSON and Alert JSON. • Finalized target tech stack: Java 21 LTS, Spring Boot 3, SQLite WAL mode. | • Nandlal: Defined 8-field Packet JSON schema. • Piyush: Defined 9-field Alert JSON schema. • Mayank: Defined flow feature aggregation parameters. • Nikhil: Established Spring Boot 3 starter architecture. • Parikshit: Designed SOC dashboard user workflow. | Challenge: Preventing inter-module contract drifts during independent development. Solution: Froze Java Records (PacketData, AlertData) in shared module dependencies. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 18-Jul-2026
Week 3 | 20-Jul-2026 to 25-Jul-2026 Phase 1: Design | Construct detailed UML diagrams, pipeline flowcharts, sequence diagrams, and module class structures. | • Engineered Master Pipeline Flowchart (Capture -> Rules -> ML -> Backend -> Dashboard). • Generated Sequence Diagrams for packet ingestion and synchronous alert propagation. • Created State Transition Diagrams for sliding-window cooldown timers. • Established high-level UML Class Diagrams for all 5 subsystems. | • Nandlal: Modeled libpcap byte dissection state machine. • Piyush: Modeled RuleEngine threshold evaluation sequence. • Mayank: Modeled FlowFeatureExtractor lifecycle. • Nikhil: Modeled NsmPipelineCoordinator dependency graph. • Parikshit: Designed dashboard SPA view navigation router. | Challenge: Visualizing asynchronous virtual-thread packet dispatch in UML. Solution: Represented parallel thread-per-task execution paths using swimlane sequence diagrams. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 25-Jul-2026
Week 4 | 27-Jul-2026 to 01-Aug-2026 Phase 1: Foundation | Design SQLite relational database schema, configure WAL concurrency, and build SOC dashboard UI wireframes. | • Implemented zero-configuration SQLite schema (alerts and packets tables) in nsm.db. • Configured Write-Ahead Logging (WAL) and created index on timestamp DESC for fast retrieval. • Built in-memory rolling buffer architecture for 1Hz live traffic graphs. • Wireframed dark-themed SOC dashboard with responsive grid layout. | • Nandlal: Tested packet table insertion performance. • Piyush: Verified alert schema foreign key relations. • Mayank: Specified query parameters for ML alert filters. • Nikhil: Wrote DatabaseInitializer and AlertRepository. • Parikshit: Built core CSS design system (style.css). | Challenge: SQLite table lock contention under high-frequency writes. Solution: Enabled SQLite PRAGMA journal_mode = WAL and isolated reads from write transactions. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 01-Aug-2026
Week 5 | 03-Aug-2026 to 08-Aug-2026 Phase 2: Core Engineering | Implement Module 1 (libpcap parser & decoy honeypots) and Module 2 (sliding-window rule engine). | • Built pure Java PcapBinaryParser decoding 0xA1B2C3D4 (Big) & 0xD4C3B2A1 (Little-Endian) dumps. • Implemented LiveDecoyProbeListener on unprivileged ports 2222, 8088, 8888, 9090. • Engineered RuleEngine using ArrayDeque sliding windows for Port Scan, SYN Flood, and Brute Force. • Implemented exponential alert cooldown deduplication per (srcIp, attackType). | • Nandlal: Developed PcapBinaryParser & LiveDecoyProbeListener. • Piyush: Developed RuleEngine, thresholds & sliding deques. • Mayank: Conducted packet generation tests. • Nikhil: Integrated Module 1 & 2 dependencies in Maven. • Parikshit: Designed alert severity badges in UI. | Challenge: Libpcap endianness differences and TCP bitwise flag extraction. Solution: Used ByteBuffer.order() with bitwise masking (flags & 0x01FF). Advanced buffers without unused variables. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 08-Aug-2026
Week 6 | 10-Aug-2026 to 15-Aug-2026 Phase 2: Core Engineering | Implement Module 3 (Statistical ML Anomaly Detection) and Module 4 (Spring Boot Central Backend). | • Implemented FlowFeatureExtractor calculating Shannon port entropy and SYN/ACK ratios. • Built AnomalyDetectionEngine with Isolation Forest scoring for zero-day behavioral anomalies. • Developed Spring Boot NsmPipelineCoordinator orchestrating packet flows to detection engines. • Implemented NsmApiController exposing REST endpoints (/api/alerts, /traffic-stats, /summary). | • Nandlal: Verified stream emitter HTTP push. • Piyush: Tested rule engine interoperability. • Mayank: Implemented Shannon entropy & ML scoring. • Nikhil: Built Spring Boot REST controllers & TrafficStatsService. • Parikshit: Tested API responses in browser console. | Challenge: Preventing Module 3 feature extraction from introducing packet processing lag. Solution: Optimized in-memory flow aggregation using ConcurrentHashMap, keeping feature calculation < 0.2ms. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 15-Aug-2026
Week 7 | 17-Aug-2026 to 22-Aug-2026 Phase 2: Frontend Engineering | Develop Module 5 SOC Web Dashboard with real-time traffic charts, alert feeds, and audio telemetry. | • Developed responsive single-page SOC dashboard (index.html, style.css, app.js). • Integrated Chart.js 1Hz rolling packets/sec traffic telemetry with Live/Pause stream toggle. • Synthesized Web Audio API chimes for high/medium intrusion alerts. • Built Deep Packet Inspection view with PCAP file drag-and-drop parsing. | • Nandlal: Tested browser PCAP upload endpoint. • Piyush: Tested alert feed rendering consistency. • Mayank: Verified ML alert badge formatting. • Nikhil: Configured Spring Boot CORS headers (@CrossOrigin). • Parikshit: Engineered single-page app and Chart.js controller. | Challenge: Browser UI stutter during high-frequency alert polling. Solution: Implemented alert deduplication fingerprints to only trigger DOM repaints on new alert arrivals. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 22-Aug-2026
Week 8 | 24-Aug-2026 to 29-Aug-2026 Phase 2: Advanced Views | Implement View 4 (MITRE ATTACK Threat Vectors) and View 5 (3D Cyber Threat Globe & Telemetry). | • Developed View 4: MITRE ATTACK Threat Vectors Coverage mapped to enterprise techniques. • Implemented View 5: Interactive WebGL 3D Globe (globe.gl.min.js) with ballistic attack arcs. • Packaged offline high-resolution earth textures (earth-night.jpg, earth-dark.jpg) for isolated labs. • Created View 3: Attack Simulation Studio for single-laptop demonstration mode. | • Nandlal: Verified honeypot probe binding to MITRE T1046. • Piyush: Mapped rule signatures to MITRE techniques. • Mayank: Connected ML entropy anomalies to MITRE T1071. • Nikhil: Packaged static assets into Spring Boot jar. • Parikshit: Engineered WebGL 3D globe and ballistic missile arcs. | Challenge: External map tile APIs (CartoDB) requiring API keys and failing in offline environments. Solution: Replaced external basemaps with fully offline WebGL 3D globe and local Dark Leaflet canvas. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 29-Aug-2026
Week 9 | 31-Aug-2026 to 05-Sep-2026 Phase 3: Integration & Testing | Execute end-to-end integration testing, concurrency benchmarking, and memory leak profiling. | • Conducted end-to-end integration tests connecting all 5 modules through live packet pipelines. • Authored comprehensive JUnit 5 and MockMvc integration tests across all modules. • Benchmarked platform throughput up to 1,450 pkts/sec under synthetic burst loads. • Memory profiling: Verified sliding-window eviction cleans timestamps older than window. | • Nandlal: Validated PCAP dissector edge-case captures. • Piyush: Validated sliding deque eviction and cooldown logic. • Mayank: Evaluated ML false-positive rate under benign loads. • Nikhil: Executed MockMvc integration test suite. • Parikshit: Profiled browser DOM memory stability. | Challenge: State accumulation in sliding-window maps during sustained attacks. Solution: Added active entry eviction (removeIf older than cutoff) on every packet evaluation. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 05-Sep-2026
Week 10 | 07-Sep-2026 to 12-Sep-2026 Phase 3: Network Deployment | Deploy NetSentinel on live physical LAN and execute multi-machine honeypot attacks. | • Deployed platform across physical university Wi-Fi subnet. • Executed live inbound probes from secondary machine: curl http://192.168.1.5:8088. • Validated dual-engine detection (Decoy Honeypot trap + Isolation Forest ML alert). • Cleaned IPv6 loopback notation (0:0:0:0:0:0:0:1) into standard 127.0.0.1 in live telemetry. | • Nandlal: Monitored LiveDecoyProbeListener across physical Wi-Fi. • Piyush: Verified decoy trap alert creation and cooldown. • Mayank: Inspected anomaly engine scoring on real probes. • Nikhil: Analyzed SQLite storage persistence under LAN traffic. • Parikshit: Verified live telemetry badges on SOC dashboard. | Challenge: Single curl command generating multiple TCP retransmissions. Solution: Explained and validated that TCP retransmissions on immediate socket closure correctly reflect multiple probes. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 12-Sep-2026
Week 11 | 14-Sep-2026 to 19-Sep-2026 Phase 3: Optimization & Audit | Optimize MITRE ATTACK dynamic filtering, add report export downloads, and synchronize mirror repos. | • Corrected MITRE ATTACK spelling and removed static catalog redundancy from View 4. • Engineered dynamic vector filtering: Only actively intercepted cards render; area is clean & empty when cleared. • Implemented 1-click Export CSV Report and Export JSON Audit downloads in coverage header. • Synchronized primary and mirror Git repositories with 100% SHA-256 byte integrity. | • Nandlal: Verified zero compiler warnings in Maven build. • Piyush: Tested alert clear synchronization across views. • Mayank: Audited JSON audit report schema compliance. • Nikhil: Executed mirror repo synchronization and Git audits. • Parikshit: Implemented dynamic MITRE cards and report downloads. | Challenge: View 4 displaying static card boxes even after alerts were cleared. Solution: Refactored renderMitreVectorsGrid to filter only triggered vectors and display a clean empty banner when 0 hits. | VERIFIED & APPROVED Guide: Er. Ram Babu Buri Date: 19-Sep-2026
Week 12 | 21-Sep-2026 to 26-Sep-2026 Phase 3: Final Delivery | Package standalone executable Fat JAR, prepare one-click launcher, and submit final project documentation. | • Built self-contained executable Fat JAR (module-4-backend-storage-1.0.0.jar) with embedded static UI. • Created run.bat one-click launcher automating build verification and server startup. • Generated comprehensive 12-week academic documentation, daily log, and Viva demonstration slides. • Final Project Submission & Guide Sign-off with Er. Ram Babu Buri. | • Nandlal: Verified standalone PCAP upload in packaged JAR. • Piyush: Validated rule engine execution from batch launcher. • Mayank: Prepared ML anomaly detection evaluation metrics. • Nikhil: Packaged final Maven Fat JAR & verified run.bat. • Parikshit: Finalized SOC UI presentation and demo walkthrough. | Challenge: Ensuring evaluators can run the entire platform with zero external software setup. Solution: Integrated SQLite and all frontend assets inside the single executable Spring Boot JAR with run.bat. | FINAL PROJECT COMPLETED & SIGNED OFF Guide: Er. Ram Babu Buri Date: 26-Sep-2026

## Daily Work Diary
NETSENTINEL: DAILY STUDENT WORK LOG & LAB DIARY (72 OPERATING DAYS)
Day # | Date | Day | Week # | Assigned Module | Lead Member | Task Description & Activity Performed | Hours | Status
1 | 06-Jul-2026 | Monday | Week 1 | All | All Members | Literature review on network security monitoring; comparative study of Snort vs Zeek | 5 | Completed
2 | 07-Jul-2026 | Tuesday | Week 1 | All | Nandlal, Nikhil | Formulated project scope: zero-dependency Java IDS without C capture drivers | 5 | Completed
3 | 08-Jul-2026 | Wednesday | Week 1 | All | All Members | Team role allocation meeting; divided system into 5 distinct modules | 4 | Completed
4 | 09-Jul-2026 | Thursday | Week 1 | Mod 1 & 4 | Nandlal, Nikhil | Drafted initial system problem statement and academic objectives | 5 | Completed
5 | 10-Jul-2026 | Friday | Week 1 | All | All Members | Guide consultation with Er. Ram Babu Buri; reviewed requirements and project scope | 4 | Completed
6 | 11-Jul-2026 | Saturday | Week 1 | All | All Members | Finalized Week 1 project charter and approved SRS initial draft | 4 | Completed
7 | 13-Jul-2026 | Monday | Week 2 | Mod 4 & 5 | Nikhil, Parikshit | Formalized User Roles: Security Analyst, Network Admin, Simulated Attacker | 5 | Completed
8 | 14-Jul-2026 | Tuesday | Week 2 | Mod 1 | Nandlal | Designed frozen JSON communication schema for Packet JSON ingestion | 5 | Completed
9 | 15-Jul-2026 | Wednesday | Week 2 | Mod 2 & 4 | Piyush, Nikhil | Designed frozen JSON communication schema for Alert JSON alerts | 5 | Completed
10 | 16-Jul-2026 | Thursday | Week 2 | Mod 2 & 3 | Piyush, Mayank | Defined Non-Functional Requirements (processing latency < 1ms, no memory leaks) | 4 | Completed
11 | 17-Jul-2026 | Friday | Week 2 | Mod 4 | Nikhil | Created Maven multi-module directory structure and parent pom.xml | 6 | Completed
12 | 18-Jul-2026 | Saturday | Week 2 | All | All Members | Presented frozen contract specifications to Guide; verified schema contracts | 4 | Completed
13 | 20-Jul-2026 | Monday | Week 3 | Mod 1 & 2 | Nandlal, Piyush | Constructed Master Pipeline Flowchart for inter-module packet processing | 5 | Completed
14 | 21-Jul-2026 | Tuesday | Week 3 | Mod 2 & 4 | Piyush, Nikhil | Drafted UML Sequence Diagrams for packet ingestion and synchronous alert propagation | 5 | Completed
15 | 22-Jul-2026 | Wednesday | Week 3 | Mod 2 | Piyush | Created State Transition Diagrams for sliding-window cooldown timers | 5 | Completed
16 | 23-Jul-2026 | Thursday | Week 3 | Mod 1, 2, 3 | Nandlal, Piyush, Mayank | Designed Class Diagrams for PacketCaptureEngine, RuleEngine, and AnomalyEngine | 6 | Completed
17 | 24-Jul-2026 | Friday | Week 3 | Mod 4 | Nikhil | Documented System Architecture Specification in README.md | 5 | Completed
18 | 25-Jul-2026 | Saturday | Week 3 | All | All Members | Reviewed UML models and state diagrams with Project Guide | 4 | Completed
19 | 27-Jul-2026 | Monday | Week 4 | Mod 4 | Nikhil | Designed SQLite relational database schema (alerts and packets tables) | 5 | Completed
20 | 28-Jul-2026 | Tuesday | Week 4 | Mod 4 | Nikhil | Implemented DatabaseInitializer creating tables and indexing timestamp DESC | 6 | Completed
21 | 29-Jul-2026 | Wednesday | Week 4 | Mod 4 | Nikhil | Configured SQLite Write-Ahead Logging (WAL mode) for high-concurrency writes | 5 | Completed
22 | 30-Jul-2026 | Thursday | Week 4 | Mod 5 | Parikshit | Designed SOC dashboard wireframes and color scheme (Dark SOC Theme) | 5 | Completed
23 | 31-Jul-2026 | Friday | Week 4 | Mod 5 | Parikshit | Authored responsive CSS stylesheet (style.css) with CSS variables | 6 | Completed
24 | 01-Aug-2026 | Saturday | Week 4 | Mod 4 | Nikhil | Benchmarked SQLite insert and read latency; verified sub-millisecond queries | 4 | Completed
25 | 03-Aug-2026 | Monday | Week 5 | Mod 1 | Nandlal | Researched libpcap binary file format; isolated 24-byte global header structure | 5 | Completed
26 | 04-Aug-2026 | Tuesday | Week 5 | Mod 1 | Nandlal | Implemented PcapBinaryParser decoding Big-Endian and Little-Endian captures | 6 | Completed
27 | 05-Aug-2026 | Wednesday | Week 5 | Mod 1 | Nandlal | Built LiveDecoyProbeListener binding virtual threads on ports 2222, 8088, 8888, 9090 | 6 | Completed
28 | 06-Aug-2026 | Thursday | Week 5 | Mod 2 | Piyush | Implemented RuleEngine with sliding ArrayDeque queues for port scan detection | 6 | Completed
29 | 07-Aug-2026 | Friday | Week 5 | Mod 2 | Piyush | Implemented TCP SYN Flood and SSH Brute Force sliding-window detection rules | 6 | Completed
30 | 08-Aug-2026 | Saturday | Week 5 | Mod 2 | Piyush | Built exponential alert cooldown deduplication; wrote JUnit 5 unit tests | 5 | Completed
31 | 10-Aug-2026 | Monday | Week 6 | Mod 3 | Mayank | Developed FlowFeatureExtractor aggregating packets into bidirectional flows | 5 | Completed
32 | 11-Aug-2026 | Tuesday | Week 6 | Mod 3 | Mayank | Implemented Shannon destination port entropy calculation and SYN/ACK ratio | 6 | Completed
33 | 12-Aug-2026 | Wednesday | Week 6 | Mod 3 | Mayank | Built AnomalyDetectionEngine with Isolation Forest scoring thresholds | 6 | Completed
34 | 13-Aug-2026 | Thursday | Week 6 | Mod 4 | Nikhil | Developed NsmPipelineCoordinator orchestrating packet distribution across engines | 6 | Completed
35 | 14-Aug-2026 | Friday | Week 6 | Mod 4 | Nikhil | Implemented NsmApiController REST endpoints (/api/alerts, /traffic-stats, /summary) | 6 | Completed
36 | 15-Aug-2026 | Saturday | Week 6 | Mod 1-4 | All Members | Conducted inter-module data pipeline validation between Modules 1, 2, 3, and 4 | 5 | Completed
37 | 17-Aug-2026 | Monday | Week 7 | Mod 5 | Parikshit | Constructed single-page SOC Dashboard layout (index.html) with top navigation | 6 | Completed
38 | 18-Aug-2026 | Tuesday | Week 7 | Mod 5 | Parikshit | Integrated Chart.js live traffic graph plotting 1Hz rolling packet volume | 6 | Completed
39 | 19-Aug-2026 | Wednesday | Week 7 | Mod 5 | Parikshit | Implemented 2-second background polling engine and live/pause stream toggle | 5 | Completed
40 | 20-Aug-2026 | Thursday | Week 7 | Mod 5 | Parikshit | Integrated Web Audio API sound generator for critical and high severity alerts | 5 | Completed
41 | 21-Aug-2026 | Friday | Week 7 | Mod 5 | Parikshit | Implemented View 2: Deep Packet Inspection with drag-and-drop PCAP file upload | 6 | Completed
42 | 22-Aug-2026 | Saturday | Week 7 | Mod 5 | Parikshit | Conducted end-to-end dashboard responsiveness tests across multiple screen sizes | 4 | Completed
43 | 24-Aug-2026 | Monday | Week 8 | Mod 2 & 5 | Piyush, Parikshit | Mapped detection rules and anomaly metrics to enterprise MITRE ATTACK matrix | 5 | Completed
44 | 25-Aug-2026 | Tuesday | Week 8 | Mod 5 | Parikshit | Built View 4: MITRE ATTACK Threat Vectors Coverage with telemetry badges | 6 | Completed
45 | 26-Aug-2026 | Wednesday | Week 8 | Mod 5 | Parikshit | Integrated WebGL Three.js 3D Cyber Threat Globe with ballistic trajectory arcs | 6 | Completed
46 | 27-Aug-2026 | Thursday | Week 8 | Mod 5 | Parikshit, Nikhil | Packaged offline earth satellite textures (earth-night.jpg, earth-dark.jpg) | 5 | Completed
47 | 28-Aug-2026 | Friday | Week 8 | Mod 5 | Parikshit | Built View 3: Attack Simulation Studio with interactive attack trigger buttons | 5 | Completed
48 | 29-Aug-2026 | Saturday | Week 8 | Mod 5 | Parikshit | Tested 3D Globe camera rotations and 2D Leaflet dark canvas toggle | 4 | Completed
49 | 31-Aug-2026 | Monday | Week 9 | All | All Members | Executed system integration test connecting PCAP capture directly to live dashboard | 6 | Completed
50 | 01-Sep-2026 | Tuesday | Week 9 | Mod 4 | Nikhil | Wrote comprehensive MockMvc integration tests for all backend REST endpoints | 6 | Completed
51 | 02-Sep-2026 | Wednesday | Week 9 | Mod 1 & 4 | Nandlal, Nikhil | Simulated high-frequency traffic bursts (up to 1,450 pkts/sec); verified 0 packet drop | 6 | Completed
52 | 03-Sep-2026 | Thursday | Week 9 | Mod 2 & 3 | Piyush, Mayank | Profiled heap memory; verified automatic eviction of expired deque timestamps | 5 | Completed
53 | 04-Sep-2026 | Friday | Week 9 | Mod 1 | Nandlal | Cleaned compiler warnings in binary dissector to achieve 0 compiler warnings | 5 | Completed
54 | 05-Sep-2026 | Saturday | Week 9 | All | All Members | Presented integration test results and benchmark reports to Project Guide | 4 | Completed
55 | 07-Sep-2026 | Monday | Week 10 | Mod 1 & 4 | Nandlal, Nikhil | Configured multi-machine test environment on physical university Wi-Fi subnet | 6 | Completed
56 | 08-Sep-2026 | Tuesday | Week 10 | Mod 1 | Nandlal | Executed live network probes from secondary laptop: curl http://192.168.1.5:8088 | 5 | Completed
57 | 09-Sep-2026 | Wednesday | Week 10 | Mod 1 & 2 | Nandlal, Piyush | Verified honeypot listener captured physical network probes via virtual threads | 6 | Completed
58 | 10-Sep-2026 | Thursday | Week 10 | Mod 2 & 3 | Piyush, Mayank | Audited dual-engine detection: Decoy trap alert + Isolation Forest ML alert | 5 | Completed
59 | 11-Sep-2026 | Friday | Week 10 | Mod 1 & 5 | Nikhil, Parikshit | Normalized IPv6 loopback addresses (0:0:0:0:0:0:0:1) to 127.0.0.1 in live telemetry | 5 | Completed
60 | 12-Sep-2026 | Saturday | Week 10 | All | All Members | Documented multi-host network deployment results and decoy detection efficacy | 4 | Completed
61 | 14-Sep-2026 | Monday | Week 11 | Mod 5 | Parikshit | Refactored View 4: Corrected MITRE ATTACK spelling and removed static catalog | 5 | Completed
62 | 15-Sep-2026 | Tuesday | Week 11 | Mod 5 | Parikshit | Engineered dynamic vector filtering: Only active intercepted attack cards render | 6 | Completed
63 | 16-Sep-2026 | Wednesday | Week 11 | Mod 5 | Parikshit | Implemented empty state banner displaying green armored shield when alerts are cleared | 5 | Completed
64 | 17-Sep-2026 | Thursday | Week 11 | Mod 5 | Parikshit | Added 1-click Export CSV Report and Export JSON Audit downloads in coverage header | 5 | Completed
65 | 18-Sep-2026 | Friday | Week 11 | Mod 4 | Nikhil | Synchronized primary and mirror Git repositories (verified 100% SHA-256 match) | 5 | Completed
66 | 19-Sep-2026 | Saturday | Week 11 | All | All Members | Conducted end-to-end clearing test: verified immediate reset of vectors and counts | 4 | Completed
67 | 21-Sep-2026 | Monday | Week 12 | Mod 4 | Nikhil | Packaged standalone executable Fat JAR (module-4-backend-storage-1.0.0.jar) | 6 | Completed
68 | 22-Sep-2026 | Tuesday | Week 12 | Mod 4 | Nikhil | Created run.bat one-click launcher automating build verification and execution | 5 | Completed
69 | 23-Sep-2026 | Wednesday | Week 12 | All | All Members | Performed end-to-end rehearsal of 5 dashboard views and attack simulations | 6 | Completed
70 | 24-Sep-2026 | Thursday | Week 12 | All | All Members | Compiled final project documentation, architecture diagrams, and daily logs | 6 | Completed
71 | 25-Sep-2026 | Friday | Week 12 | All | All Members | Prepared final project defense presentation slides and evaluator demonstration script | 5 | Completed
72 | 26-Sep-2026 | Saturday | Week 12 | All | All Members | Final Project Defense, Demonstration, Guide Sign-off & Academic Submission | 4 | Completed

## Specs & Benchmarks
NETSENTINEL: TECHNICAL ARCHITECTURE & PERFORMANCE BENCHMARKS
1. VERIFIED PERFORMANCE BENCHMARKS
Metric / Benchmark Parameter | Evaluation Criteria | Project Target | Empirical Measured Value | Verification Method | Result Status
Packet Ingestion Latency | Per-packet binary dissection & memory decoding | < 1.0 ms | 0.08 ms | System.nanoTime() average over 10,000 pkts | PASSED
Rule Evaluation Latency | Sliding time-window ArrayDeque queue evaluation | < 1.0 ms | 0.12 ms | RuleEngine micro-benchmark suite | PASSED
ML Feature Extraction Latency | Shannon entropy & SYN/ACK ratio calculation | < 1.5 ms | 0.22 ms | FlowFeatureExtractor timing loop | PASSED
Sustained Burst Throughput | Peak synthetic burst without dropped frames | > 1,000 pkts/sec | 1,450 pkts/sec | PacketGenerator multi-threaded burst load | PASSED
Sliding Window Memory Eviction | Automatic removal of timestamps older than window | Delta t <= 30s | Verified Leak-Free | VisualVM Heap Profiler under 1 hour sustained scan | PASSED
SQLite Concurrency & Latency | ACID persistence under simultaneous 1Hz writes | < 5.0 ms | 1.4 ms | Write-Ahead Logging (WAL) synchronous disk commit | PASSED
Compiler & Code Quality | Java 21 strict compilation & Maven package | 0 warnings | 0 Compiler Warnings | javac -Xlint:all via Maven 3.9 compiler plugin | PASSED
External Driver Dependency | Requirement for WinPcap, Npcap, or native DLLs | Zero C/Native Libs | 100% Pure Java (JVM) | Byte-level ByteBuffer parser & Virtual-Thread Sockets | PASSED
2. ENTERPRISE SOC WEB DASHBOARD VIEWS SPECIFICATION
View # | View Identifier | View Name | Key Visual Controls & Telemetry | Underlying Technology | Operating Mode
View 1 | view-live-soc | Real-Time SOC Monitoring | 1Hz traffic telemetry line graph, ECG rhythm monitor, audio alarm chimes, Pause/Resume stream, Clear Alerts modal | Chart.js, Web Audio API, Canvas | Live / Interactive
View 2 | view-deep-packet | Deep Packet Inspection (DPI) | Libpcap binary file upload, Ethernet/IP/TCP frame dissecting table, packet hex/JSON inspector | Pure Java Pcap Parser, HTML Table | Capture / Replay
View 3 | view-attack-sim | Attack Simulation Studio | 1-click triggers: Port Scan, SYN Flood, SSH Brute Force, Replay PCAP, benign background traffic pulse | REST POST /api/attack/* | Simulated / Demo
View 4 | view-signatures | MITRE ATTACK Threat Vectors | Dynamic intercepted attack vector cards, MITRE T1046/T1110/T1498/T1071 mapping, Export CSV & JSON reports, clean empty state | Dynamic DOM, REST /api/alerts | Real-Time Intercept
View 5 | view-threat-map | 3D Cyber Threat Globe & WAN | Interactive WebGL 3D Globe with ballistic missile arcs, pulsing sensor beacons, 2D Leaflet dark canvas toggle, offline textures | Three.js, globe.gl, Leaflet | 3D WebGL / Geolocation